## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 20
PROJECT NAME | Slearn
PROJECT MENTOR (sponsor) | shankar foundation
TEAM MEMBERS | arya mirani
vaishnavi k
dev patel
manan trivedi
vruddhi shah

## Status
PROJECT NUMBER | 20
PROJECT NAME | Slearn
PROJECT MENTOR (sponsor) | Santhosh
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 17)
[Jan 16] Set a meeting with the client | Coordination | arya | 1.5 | 1.5 | Done | onboarding of the team with the client and knowing the process | 0 | 0
[Jan 16] Updated design requirements after client meeting | Documentation | vaishnavi | 1 | 1.05 | Done | update the design requirements according to client feedback, and divide work among team members | -0.05 | 4.7619
Week 2 (January 18 - January 24)
[jan 18] restructure repository | Documentation | arya |  |  | Done | setup branches and connect to vercel
[jan 18] changes requested by client in meeting | Project Progress | arya |  |  | Done | UI changes
[jan 19] changes requested by client in meeting | Project Progress | manan |  |  | Done | UI changes
changes requested by the clients - Increse the Font sizes in Some modules , Changes some Submit Button | Project Progress | vruddhi | 1 | 1 | Done | UI changes | 0 | 0
[jan 21] changes requested by client in meeting | Project Progress | dev |  |  | Done | UI changes
[Jan 22] client requested changes – color changes, navigation changes between vocabulary exercises | Project Progress | vaishnavi | 1 | 2.75 | Done | UI changes | -1.75 | 63.6364
[jan 23] Pushed the code to vercel for sending to clients, made website responsive for phone and tablet | Coordination | arya |  |  | Done
Meeting 2 with client [Feb 23] | Coordination | all | 1 | 1 | Done | updated client on changes made; documented feedback to further changes | 0 | 0
Week 3 (January 25 – January 31)
allocated work in implementing further modules | Coordination | dev, vruddhi ,manan, vaishnavi | 1 | 1 | Done |  | 0 | 0
project synopsis | Documentation | dev |  |  | Done
Week 4(Feb 1 - Feb 7)
[Feb 1] make backend database using supabase | Project Progress | arya | 10 |  | Ongoing
[Feb 1] created new modules – evs | Project Progress | manan |  |  | Done
[feb 2] created new modules – english | Project Progress | vruddhi | 2 | 3 | Done | add new modules in English | -1 | 33.3333
[feb 2-3] created new modules (math word problems, english read words), added exercises to evs module | Project Progress | vaishnavi | 2 | 2.5 | Done |  | -0.5 | 20
[feb 3] Team Internal meeting | Coordination | all | 2 | 2 | Done | Discussed navigation issues and variations in module implementation; resplit tasks to ensure uniformity among modules | 0 | 0
[feb 3] created new modules - english | Project Progress | dev |  |  | Done
[feb 3] refactored and organized codebase for vercel and grade-wise navigation | Project Progress | manan |  |  | Done
navigation changes – dashboard | Project Progress | dev |  |  | Done
Go to Shankar Foundation School [Feb 4] | Coordination | All | 2 | 3 | Done | visited the school and saw the process of teaching | -1 | 33.3333
[feb 5] main page dropdown menus, navigation between modules | Project Progress | vruddhi | 1 | 1.5 | Done | added dropdown menu for the grades on the main page which further nevigates to the menu of specific subject of that grade and which will nevigate to exersices of that subject . | -0.5 | 33.3333
Further exercise changes in modules – english | Project Progress | dev |  |  | Done
exercise changes in modules – math | Project Progress | arya | 1 | 1 | Done |  | 0 | 0
[feb 7] resizing and rearranging evs | Project Progress | manan |  |  | Done
Week 5 (Feb 8 – Feb 14)
Updating project plan, updating status tracker since first meet | Documentation | vaishnavi | 3 |  | In progress
Week 6 (Feb 15 – Feb 21)